Project Summary

| Progress Report 4/13/2026 Whale–Vessel Disturbance Risk California Coast (2020–2025) | Team: Charlotte JinHyuk Son Jeongmin An Yeobi Hobson Consultant: Prof Michael Mann |
| --- | --- |
| Tasks Completed | - Loaded and cleaned the three core datasets used in the project: NOAA WhaleWatch, Global Fishing Watch AIS, and the TIGER/Line California boundary. - For NOAA WhaleWatch, loaded all monthly CSV files from 2020–2025, combined them into a single table, and checked the record for missing months. - Cleaned and validated the combined WhaleWatch table by verifying longitude formatting and retaining rows with valid model output. - Built the study area as a 200 km coastal buffer around California using EPSG:3310 for distance-based operations and reprojected it to EPSG:4326 for joining. - Constructed a 0.25° analysis fishnet aligned to the WhaleWatch lattice and retained cells intersecting the buffered study area. - Snapped 4.37M rows of GFW vessel data to the 0.25° WhaleWatch grid and summed vessel hours across flags by vessel type and speed band. - Computed a literature-based speed-weighted vessel exposure score (Conn & Silber 2013; van der Hoop et al. 2015). - Collapsed vessel exposure to one record per (cell, year, month) and joined it to the cleaned WhaleWatch table. - Calculated the composite monthly risk score (whale presence × weighted vessel exposure) and a log-dampened risk variant for downstream analysis. - Exported the resulting risk dataset as CSV and GPKG files for the next stages of spatial (LISA) and temporal analysis. - Organized the workflow into two notebooks: one for WhaleWatch loading/combining and one for risk calculation and analysis-ready data preparation. |
| Tasks Planned for next reporting period | - Run Global Moran's I and Local Moran (LISA) monthly for 2020–2025 using Queen contiguity weights. - Generate LISA cluster labels and hotspot maps (HH/LL/HL/LH/ns). - Produce monthly, seasonal, and year-over-year risk summaries and classify hotspot trajectories. - Interpret shifts in high-risk locations across years. - Build the interactive Folium time-slider map of monthly risk. - Prepare the final report, presentation, and supporting visualizations. |

Progress Summary

| Milestone | % | Comments |
| --- | --- | --- |
| Review of Literature | 100 | Reviewed whale–vessel collision literature, including Conn & Silber (2013) and van der Hoop et al. (2015), to justify the 10-knot lethal-strike threshold and the step-function speed-weighting scheme used in the exposure score. |
| Data collection | 100 | Collected NOAA WhaleWatch monthly model output (2020–2025, 0.25° grid), Global Fishing Watch AIS vessel presence (2020–2025, 0.1° grid, filtered by vessel type and speed band), and the TIGER/Line 2024 U.S. state boundary shapefile. |
| Development of database & summary statistics | 100 | All inputs were organized and summarized to a common 0.25° cell–month unit. WhaleWatch longitudes were converted from 0–360 to –180/180 and rows without model output were dropped; the California polygon was reprojected from NAD83 (EPSG:4269) to California Albers (EPSG:3310), buffered by 200 km, and reprojected back to WGS84 (EPSG:4326); the 4.37M-row GFW table was snapped to the 0.25° lattice and aggregated across flags to produce vessel hours by speed band and vessel type, which were then converted into a speed-weighted vessel exposure score, collapsed to one record per (cell, year, month), and joined to the cleaned WhaleWatch table. |
| Statistical Analysis | 60 | Computed a speed-weighted vessel exposure score and defined composite monthly risk as whale presence probability × weighted exposure, with a log-dampened variant to control heavy-tailed exposure. LISA, hotspot classification, and temporal summary analysis have not yet been run and are planned for the next stage. |
| Reports | 25 | Methodology and README have been finalized, and this progress report has been submitted for the April reporting period. |
| Workshop | 0 |  |
| Final Meetings | 0 |  |